## 📊 Dashboard
InsuredCan.ca — 90-Day SEO/GEO/AEO Progress Dashboard
Track weekly KPIs · Update every Monday · Start Date: April 10, 2026
📈 WEEKLY KPI TRACKER (Update every Monday)
Week | Dates | GSC Impressions | GSC Clicks | CTR % | Avg Position | Indexed Pages | Backlinks | Top-10 Keywords | Top-3 Keywords | DA Score | Notes
Week 1 | Apr 10–Apr 16
Week 2 | Apr 17–Apr 23
Week 3 | Apr 24–Apr 30
Week 4 | May 01–May 07
Week 5 | May 08–May 14
Week 6 | May 15–May 21
Week 7 | May 22–May 28
Week 8 | May 29–Jun 04
Week 9 | Jun 05–Jun 11
Week 10 | Jun 12–Jun 18
Week 11 | Jun 19–Jun 25
Week 12 | Jun 26–Jul 02
Week 13 | Jul 03–Jul 09
🏁 PHASE MILESTONES & STATUS
Phase | Focus | Days | Key Actions | Status | % Complete | Notes
Phase 1 | Rapid Indexing + GSC | Days 1–7 | Submit 70+ URLs, sitemap, GSC setup | Not Started | 0%
Phase 2 | Directory Authority (Local SEO) | Days 5–7 | Yelp, YP, 411, Cylex, n49 listings | Not Started | 0%
Phase 3 | Backlink Seeding | Days 8–16 | 5 Medium + 10 Quora + 5 Reddit | Not Started | 0%
Phase 4 | Social Distribution | Days 15–22 | 10 LinkedIn + 10 Facebook posts | Not Started | 0%
Phase 5 | Brand/Entity Signals | Days 22–30 | GMB, schema, NAP consistency | Not Started | 0%
Phase 6 | CTR Optimization | Days 22–25 | Title tags + meta descriptions live | Not Started | 0%
Phase 7 | Content Expansion | Days 31–50 | 3 new blogs + 3 city pages + AEO | Not Started | 0%
Phase 8 | Authority Building | Days 46–60 | Guest posts, HARO, PR outreach | Not Started | 0%
Phase 9 | AEO Optimization | Days 55–75 | FAQ/HowTo schema, PAA, voice search | Not Started | 0%
Phase 10 | Review + Scale | Days 76–90 | Audit, optimize winners, next quarter plan | Not Started | 0%
🎯 TOP 14 TARGET KEYWORDS — RANKING SNAPSHOT
Keyword | Target Page | Volume/mo | Target Rank | Week 4 Rank | Week 8 Rank | Week 13 Rank | Status
life insurance ontario | /life-insurance-ontario | 1,600+ | Top 5
life insurance toronto | /life-insurance-toronto | 1,300+ | Top 5
best life insurance canada | / | 2,400+ | Top 10
critical illness insurance canada | /critical-illness-insurance | 800+ | Top 10
super visa insurance canada | /blog/super-visa-insurance-canada | 1,200+ | Top 5
cheapest life insurance canada 2026 | /blog/cheapest-life-insurance-canada-2026 | 800+ | Top 3
life insurance mississauga | /life-insurance-mississauga | 500+ | Top 3
life insurance brampton | /life-insurance-brampton | 400+ | Top 3
disability insurance ontario | /disability-insurance | 600+ | Top 10
funeral insurance canada | /funeral-insurance | 400+ | Top 5
insurance broker ontario | /insurance-broker-canada | 600+ | Top 10
life insurance newcomers canada | /newcomers | 400+ | Top 5
term vs whole life canada | /compare/term-vs-whole-life | 700+ | Top 10
how much life insurance canada | /blog/how-much-life-insurance-canada | 500+ | Top 5

## 📅 90-Day Action Plan
InsuredCan.ca — 90-Day Daily Action Plan (SEO / GEO / AEO)
Each row = one action item. Update STATUS as you complete. Ask Claude for execution help on any item.
Day | Date | Week | Phase | Category | Action Item | WHY IT MATTERS (Learn This) | Execution Notes / How-To | Priority | Time (min) | Status
1 | Apr 10 | Week 1 | Phase 1 | Technical SEO | Set up Google Search Console — verify insuredcan.ca property | GSC is your #1 free tool. It tells Google you own the site, shows which queries bring traffic, and lets you request indexing. Without it, you're flying blind. | Go to search.google.com/search-console → Add property → Select 'Domain' → Copy the DNS TXT record → Add it to your domain DNS settings (Cloudflare or GoDaddy) | 🔴 High | 30 | ⏳ Pending
1 | Apr 10 | Week 1 | Phase 1 | Technical SEO | Submit sitemap.xml in Google Search Console | A sitemap is a map of your site for Google's crawler. Submitting it tells Google exactly what pages exist and helps them crawl and index faster. | In GSC → Sitemaps (left sidebar) → Enter 'sitemap.xml' → Submit → Confirm status shows 'Success' | 🔴 High | 10 | ⏳ Pending
2 | Apr 11 | Week 1 | Phase 1 | Technical SEO | Submit Tier 1 URLs to GSC (15 priority pages) | Manual indexing requests tell Google 'this page is important, crawl it NOW.' This bypasses the normal crawl queue and can get pages indexed within 24–72 hours. | GSC → URL Inspection → Paste URL → 'Request Indexing'. Do: homepage, /life-insurance-ontario, /life-insurance-toronto, /life-insurance-mississauga, /life-insurance-brampton, /life-insurance-hamilton, /life-insurance-ottawa, /life-insurance, /critical-illness-insurance, /critical-illness-insurance-ontario, /funeral-insurance, /cost-life-insurance-ontario, /term-life-insurance, /whole-life-insurance, /disability-insurance | 🔴 High | 45 | ⏳ Pending
3 | Apr 12 | Week 1 | Phase 1 | Technical SEO | Submit Tier 2 URLs to GSC (health, mortgage, city pages, audience pages) | Every page needs to be discoverable. City pages and audience pages (/newcomers, /families, /self-employed) are high-intent for local searches. | GSC URL Inspection — submit: /health-insurance, /mortgage-insurance, /travel-insurance, /life-insurance-markham, /life-insurance-kitchener-waterloo, /life-insurance-windsor, /life-insurance-oshawa, /life-insurance-barrie, /life-insurance-london-ontario, /insurance-broker-canada, /life-insurance-pr-holders, /newcomers, /families, /self-employed, /young-professionals | 🔴 High | 40 | ⏳ Pending
4 | Apr 13 | Week 1 | Phase 1 | Technical SEO | Submit comparison pages + top 5 blogs to GSC | Comparison pages (/compare/*) target high-value 'vs' queries. Blogs with '2026' in the URL have strong freshness signals that can rank quickly. | Submit: /compare/term-vs-whole-life, /compare/critical-illness-vs-disability, /compare/private-vs-ohip, /coverage-calculator, /retirement-planning, /insurance-glossary, /blog/best-life-insurance-ontario-2026, /blog/cheapest-life-insurance-canada-2026, /blog/how-much-life-insurance-canada, /blog/is-life-insurance-worth-it-canada, /blog/super-visa-insurance-canada | 🔴 High | 30 | ⏳ Pending
5 | Apr 14 | Week 1 | Phase 1 + 2 | Local SEO | Register InsuredCan on Yelp Canada | Yelp Canada is a high-authority directory that Google trusts. A Yelp listing creates a citation (consistent NAP mention) that strengthens your local authority for Ontario-based searches. | Go to biz.yelp.ca → Claim or add business → Business Name: InsuredCan → Category: Insurance Brokers → Use NAP template from the Directories sheet → Add both short and long descriptions | 🔴 High | 45 | ⏳ Pending
6 | Apr 15 | Week 1 | Phase 2 | Local SEO | Register on YellowPages Canada (yellowpages.ca) | YellowPages.ca has massive domain authority (DA 70+) and is heavily crawled by Google. A citation here passes significant local trust signals to your site. | Go to yellowpages.ca → Add a listing → Use exact NAP template. Category: Insurance Agents & Brokers, Life Insurance. Add all descriptions from the Master Plan doc | 🔴 High | 30 | ⏳ Pending
6 | Apr 15 | Week 1 | Phase 2 | Local SEO | Register on 411.ca | 411.ca is one of Canada's oldest and most trusted business directories. Citations here create consistent NAP data that Google uses to validate your business entity. | Go to 411.ca → Add business → Use exact NAP. Category: Insurance, Life Insurance Agents, Health Insurance | 🟡 Medium | 20 | ⏳ Pending
7 | Apr 16 | Week 1 | Phase 2 | Local SEO | Register on Cylex Canada (cylex.ca) + n49.com | Cylex and n49 are niche business directories that build citation breadth. More citations = stronger entity signals = better local pack ranking. | Cylex: cylex.ca → add business. n49: n49.com → add business. Use identical NAP template for both. Inconsistent NAP is one of the top local SEO mistakes. | 🟡 Medium | 40 | ⏳ Pending
7 | Apr 16 | Week 1 | Phase 1 | Technical SEO | Audit all submitted URLs in GSC — check for 'Coverage' errors | After submitting URLs, GSC may show errors: 'Crawled — not indexed', 'Excluded', or 'Redirect error'. Each error type needs a different fix. Checking early = faster resolution. | GSC → Pages → Coverage report → Filter by 'Excluded' → Screenshot for records → Note any 'Soft 404' or 'Duplicate' issues | 🟡 Medium | 20 | ⏳ Pending
8 | Apr 17 | Week 2 | Phase 3 | Backlinks | Publish Medium Article 1: 'Why Every Ontario Family Needs Life Insurance in 2026' | Medium is a high-DA platform (DA 95). Articles published there with links back to your site create DoFollow backlinks that pass PageRank. Google sees these as votes of confidence. | Go to medium.com → Write Story → Use full Article 1 text from the Master Plan → Target link: insuredcan.ca/life-insurance-ontario → Publish with tags: life insurance, ontario, insurance canada, personal finance canada | 🔴 High | 60 | ⏳ Pending
9 | Apr 18 | Week 2 | Phase 3 | Backlinks | Publish Medium Article 2: 'Critical Illness Insurance in Canada: The Coverage Most Canadians Are Missing' | Each Medium article targets a different page on your site. This spreads link equity across multiple pages, helping multiple keywords rank — not just one. | Use Article 2 text from Master Plan → Target link: /critical-illness-insurance → Tags: critical illness insurance, cancer insurance canada, financial planning canada | 🔴 High | 45 | ⏳ Pending
10 | Apr 19 | Week 2 | Phase 3 | Backlinks | Publish Medium Article 3: 'Disability Insurance for Self-Employed Canadians' | Self-employed + disability insurance is a high-intent, low-competition keyword cluster. This article targets that niche while building a backlink to /self-employed. | Use Article 3 text from Master Plan → Target link: /self-employed → Tags: self employed canada, disability insurance, freelancer canada | 🔴 High | 45 | ⏳ Pending
11 | Apr 20 | Week 2 | Phase 3 | Backlinks | Publish Medium Article 4: 'Super Visa Insurance — Everything Parents Need to Know' | Super visa insurance is a high-volume keyword (1,200+/mo) with clear commercial intent. This article targets it while linking to the blog post on that topic. | Use Article 4 text from Master Plan → Target link: /blog/super-visa-insurance-canada → Tags: super visa insurance, parents canada, immigration insurance | 🔴 High | 45 | ⏳ Pending
12 | Apr 21 | Week 2 | Phase 3 | Backlinks | Publish Medium Article 5: 'Term Life vs. Whole Life Insurance in Canada' | Comparison content ('X vs Y') is one of the highest-converting content types online. This targets a 700+/mo keyword while linking to your compare page. | Use Article 5 text → Target link: /compare/term-vs-whole-life → Tags: term life insurance, whole life insurance, insurance canada | 🟡 Medium | 45 | ⏳ Pending
13 | Apr 22 | Week 2 | Phase 3 | Backlinks | Post Quora Answers 1–5 | Quora has DA 93 and millions of active users. Answers that get upvotes can rank in Google themselves, and the links back to your site pass authority AND drive referral traffic. | Search each exact question on quora.com → Click 'Answer' → Paste your prepared answer from Master Plan → Format with line breaks → Add link naturally at the end. Q1: best life insurance ontario. Q2: life insurance cost 40yr old. Q3: newcomers qualify for life insurance. Q4: is critical illness worth it. Q5: what if I can't pay life insurance premiums | 🔴 High | 60 | ⏳ Pending
14 | Apr 23 | Week 2 | Phase 3 | Backlinks | Post Quora Answers 6–10 | Aim for 300+ word answers — Quora's algorithm promotes detailed answers. Shorter answers rarely get upvotes or SEO value. | Q6: OHIP waiting period what insurance needed. Q7: self-employed disability insurance canada. Q8: no medical life insurance canada. Q9: agent vs broker canada. Q10: is life insurance payout taxable canada — use full prepared answers from Master Plan | 🔴 High | 60 | ⏳ Pending
15 | Apr 24 | Week 3 | Phase 3 | Backlinks | Post Reddit Responses 1–3 in r/PersonalFinanceCanada | Reddit posts in r/PersonalFinanceCanada regularly rank on page 1 of Google for insurance questions. Helpful, non-spammy answers build genuine community credibility and referral traffic. | Search for active threads: 'how much life insurance do I need', 'just became PR should I get life insurance', 'self employed what if I get sick'. Reply with your prepared responses from Master Plan. Do NOT post all 5 on the same day — spread by 3+ hours or different days. | 🔴 High | 40 | ⏳ Pending
16 | Apr 25 | Week 3 | Phase 3 | Backlinks | Post Reddit Responses 4–5 in r/PersonalFinanceCanada | Consistency in community participation matters more than volume. Two quality responses per day is safer than five at once (which can look spammy to Reddit's algorithm). | Threads: 'bank life insurance vs independent' and 'what insurance do I need as 30yr old ontario'. Use prepared responses. Upvote helpful related comments first to establish credibility before posting. | 🟡 Medium | 30 | ⏳ Pending
17 | Apr 26 | Week 3 | Phase 4 | Social Media | Publish LinkedIn Posts 1–3 | LinkedIn posts with external links get lower organic reach — but insurance content (financial education) performs well with professionals. Schedule for 7–9am EST. | Post 1: Bank vs independent life insurance (link to /life-insurance-ontario). Post 2: Critical illness gap (link to /critical-illness-insurance). Post 3: Self-employed disability (link to /self-employed). Use full text from Master Plan social section. Add a professional stock photo. | 🟡 Medium | 45 | ⏳ Pending
18 | Apr 27 | Week 3 | Phase 4 | Social Media | Publish LinkedIn Posts 4–6 | LinkedIn's algorithm rewards consecutive posting. 3+ posts/week builds page momentum and gets posts shown to more of your followers' networks. | Post 4: Newcomers to Canada insurance (link to /newcomers). Post 5: Income protection math (link to /life-insurance). Post 6: Coverage Calculator CTA (link to /coverage-calculator). Schedule for 12pm EST. | 🟡 Medium | 30 | ⏳ Pending
19 | Apr 28 | Week 3 | Phase 4 | Social Media | Publish LinkedIn Posts 7–10 | Completing the first 10-post batch establishes your content baseline. LinkedIn page authority grows with consistent posting history. | Post 7: Funeral insurance (link to /funeral-insurance). Post 8: Young professionals timing (link to /young-professionals). Post 9: Term vs Whole (link to /compare/term-vs-whole-life). Post 10: Retirement planning (link to /retirement-planning). | 🟡 Medium | 30 | ⏳ Pending
20 | Apr 29 | Week 3 | Phase 4 | Social Media | Publish Facebook Posts 1–5 | Facebook posts reach a wider consumer demographic than LinkedIn. Insurance content with emotional hooks ('protect your family') performs especially well. Post at 6–8pm EST. | Post 1: Bank vs individual insurance (Ontario). Post 2: Parent protection emotional hook. Post 3: Newcomers to Canada checklist. Post 4: Critical illness gap. Post 5: Funeral costs. Add emoji, keep conversational, use images from the site. | 🟡 Medium | 40 | ⏳ Pending
21 | Apr 30 | Week 3 | Phase 4 | Social Media | Publish Facebook Posts 6–10 | Facebook's algorithm boosts posts with comments. End each post with a genuine question to drive engagement ('Does your current coverage cover this?'). | Post 6: Coverage Calculator CTA. Post 7: Self-employed disability. Post 8: Tax-free payout fact. Post 9: Toronto families GTA. Post 10: Super Visa insurance reminder. Use full text from Master Plan. | 🟡 Medium | 30 | ⏳ Pending
22 | May 01 | Week 4 | Phase 6 | On-Page SEO | Publish meta tag + title updates via Lovable for all 10 priority pages | Title tags are the #1 on-page ranking factor. Meta descriptions don't directly affect ranking but dramatically impact click-through rate (CTR). Higher CTR sends positive signals to Google. | Go to lovable.dev → InsuredCan project → Use chat: 'Update metaTitle and metaDescription for [page] to: [new title] ¦ [new description]'. Do all 10 pages from Phase 6 in the Master Plan. Then click Publish. | 🔴 High | 60 | ⏳ Pending
23 | May 02 | Week 4 | Phase 5 | Technical SEO | Fix orphan pages — add city links to Ontario hub | Orphan pages (pages with no internal links pointing to them) are nearly invisible to Google. Adding internal links creates crawl paths and distributes PageRank to these pages. | In Lovable: update /life-insurance-ontario to add grid links for Kitchener-Waterloo (/life-insurance-kitchener-waterloo), Windsor (/life-insurance-windsor), Oshawa (/life-insurance-oshawa), Barrie (/life-insurance-barrie). Already done in local code — just need to publish. | 🔴 High | 30 | ⏳ Pending
24 | May 03 | Week 4 | Phase 5 | Technical SEO | Set up Google Business Profile (GMB) for InsuredCan | Google Business Profile (formerly Google My Business) is mandatory for appearing in Google's Local Pack (the map results). Even online businesses can have a service-area listing. | Go to business.google.com → Add business → Business type: Service area business (not physical address) → Service area: Ontario, Canada → Category: Insurance broker → Add phone, website, hours, description → Verify via phone or postcard | 🔴 High | 45 | ⏳ Pending
25 | May 04 | Week 4 | Phase 5 | Technical SEO | Add FAQ schema to top 5 pages (via Lovable) | FAQ schema creates expandable Q&A sections directly in Google search results, doubling your visual real estate on the results page. This significantly boosts CTR and can trigger featured snippets. | In Lovable chat: 'Add FAQ schema markup to [page] using these questions: [paste FAQs from existing page content]'. Priority: /life-insurance-ontario, /critical-illness-insurance, /disability-insurance, /funeral-insurance, /newcomers | 🔴 High | 60 | ⏳ Pending
26 | May 05 | Week 4 | Phase 5 | AEO | Optimize top 5 pages for 'People Also Ask' (PAA) box | AEO (Answer Engine Optimization) is about structuring content so Google can extract it as a direct answer. PAA boxes appear 75%+ of SERPs and get massive visibility. | For each priority page: find the PAA questions that appear when you search the target keyword → Make sure each question is answered clearly in 40–50 words in the page content → Use H2 or H3 for the question, then direct answer in the first sentence of the paragraph | 🔴 High | 60 | ⏳ Pending
27 | May 06 | Week 4 | Phase 1 | Technical SEO | Check and fix any page speed issues (Core Web Vitals) | Google uses Core Web Vitals (loading speed, interactivity, visual stability) as a ranking factor. Pages that load slowly get penalized. Lovable-hosted sites are usually fast but worth checking. | Go to pagespeed.insights.google.com → Enter insuredcan.ca → Check scores for Mobile and Desktop → Look for: LCP (Largest Contentful Paint) < 2.5s, FID < 100ms, CLS < 0.1. Note any 'opportunities' flagged. | 🟡 Medium | 30 | ⏳ Pending
28 | May 07 | Week 4 | Phase 5 | Technical SEO | Verify all canonical tags are correct site-wide | Canonical tags tell Google which version of a page is the 'official' one. Missing or wrong canonicals cause duplicate content issues that dilute ranking power. | View source on 3-4 pages → Search for 'canonical' → Verify each canonical URL is the correct absolute URL (https://www.insuredcan.ca/page). Check that paginated pages point to the root page. | 🟡 Medium | 20 | ⏳ Pending
29 | May 08 | Week 5 | Phase 5 | Technical SEO | Submit updated sitemap after all new page publishes | After making changes and publishing, Google needs to recrawl. Resubmitting the sitemap triggers a fresh crawl of the updated site. | GSC → Sitemaps → Click existing sitemap → 'Remove' → Re-add sitemap.xml → Submit. This refreshes the crawl queue with all your new changes. | 🟡 Medium | 10 | ⏳ Pending
30 | May 09 | Week 5 | Phase 1 | Review | Week 4 Review — analyze GSC data, check ranking progress | Weekly reviews are how you measure what's working. Look at: which queries gained impressions, which pages got indexed, which CTRs improved. Adjust next week based on data. | GSC → Performance → Last 28 days → Sort by Clicks ↓. Note top 10 queries. Check Coverage — any new errors? Check Index Coverage for newly submitted pages. Log all KPIs in Dashboard sheet. | 🔴 High | 60 | ⏳ Pending
31 | May 10 | Week 5 | Phase 7 | Content | Write new blog: '7 Insurance Mistakes Canadians Make (And How to Avoid Them)' | List-style blog posts ('7 mistakes', '5 steps') earn more backlinks naturally because other sites reference them. This type of content is also highly shareable on social media. | Structure: Intro → 7 mistakes with H2 headers → Solution for each → CTA at end. Each mistake should link to a relevant service page internally. Aim for 1,200–1,500 words. Publish via Lovable. | 🟡 Medium | 90 | ⏳ Pending
32 | May 11 | Week 5 | Phase 7 | Content | Write new blog: 'Health Insurance Ontario 2026: What OHIP Doesn't Cover' | 'What OHIP doesn't cover' is a high-intent search query from Ontarians who just realized their provincial coverage has gaps. This is bottom-of-funnel traffic that converts well. | Structure: What OHIP covers → What it doesn't (dental, vision, drugs, paramedical) → How to fill the gap → Compare private plans → CTA to /health-insurance. 1,000–1,200 words. | 🟡 Medium | 90 | ⏳ Pending
33 | May 12 | Week 5 | Phase 7 | Content | Write new blog: 'Best Life Insurance for Newcomers to Canada 2026' | Newcomers to Canada is a growing demographic with 400K+ new residents annually. Content targeting their specific questions earns traffic that competitors rarely create. | Structure: What newcomers need → OHIP wait coverage → Life insurance eligibility → Super Visa for parents → PR vs work permit coverage → CTA to /newcomers. Target keyword: 'life insurance newcomers canada' | 🟡 Medium | 90 | ⏳ Pending
34 | May 13 | Week 5 | Phase 7 | Content | Publish 3 new blogs via Lovable + internal link to them from relevant pages | Publishing alone isn't enough — new pages need internal links to be discovered. Link each new blog from the most relevant service page to pass PageRank and drive crawling. | Publish all 3 blogs in Lovable. Then add links: from /health-insurance to OHIP blog, from /newcomers to newcomers blog, from Homepage to mistakes blog. Publish changes. | 🔴 High | 45 | ⏳ Pending
35 | May 14 | Week 5 | Phase 7 | GEO | Create new city page: 'Life Insurance Vaughan' | GEO optimization means creating dedicated content for geographic search queries. 'Life insurance Vaughan' has 300+/mo searches and almost no competition from authoritative insurance sites. | Use existing city page format (copy LifeInsuranceMississauga.tsx as template) → Update city name, local references, landmarks, demographics → Update metaTitle to include 'Vaughan 2026'. Add to App.tsx routes and Navbar city list. | 🟡 Medium | 60 | ⏳ Pending
36 | May 15 | Week 6 | Phase 7 | GEO | Create new city page: 'Life Insurance Richmond Hill' | Richmond Hill is one of Ontario's fastest-growing municipalities with a large newcomer population — an ideal audience for InsuredCan's services. Geo-targeted pages can rank within 2–3 weeks. | Same process as Vaughan page. Update all city-specific references. Add unique paragraph about Richmond Hill demographics (large Chinese-Canadian population — mention multilingual advisors if applicable). | 🟡 Medium | 45 | ⏳ Pending
37 | May 16 | Week 6 | Phase 7 | GEO | Create new city page: 'Life Insurance Burlington' | Burlington/Oakville corridor has high household income = higher insurance purchase intent. A dedicated page captures this traffic that currently goes to generic Ontario pages. | Same city page process. Mention proximity to Hamilton, GTA West corridor. Link from /life-insurance-ontario and /life-insurance-hamilton. | 🟢 Low | 45 | ⏳ Pending
38 | May 17 | Week 6 | Phase 7 | GEO | Publish new city pages + add them to App.tsx routes and Ontario hub | City pages only get Google traffic when they're properly routed, linked from the Ontario hub, and have their own meta tags. All three steps must be done together. | In Lovable: 'Add these new pages to the App.tsx routing and add them to the /life-insurance-ontario city grid: Vaughan (/life-insurance-vaughan), Richmond Hill (/life-insurance-richmond-hill), Burlington (/life-insurance-burlington)' | 🔴 High | 30 | ⏳ Pending
39 | May 18 | Week 6 | Phase 7 | Content | Update 5 existing blogs — add '2026' freshness signal to titles and content | Google's freshness algorithm rewards recently updated content for competitive queries. Adding '2026' to titles and updating stats in the first 100 words signals freshness without rewriting the whole page. | In Lovable: Update title and first paragraph of: BlogTermVsWhole, BlogHowMuchLifeInsurance, BlogCriticalIllnessCoverage, BlogDisabilityInsuranceSelfEmployed, BlogNoMedicalLifeInsurance. Change title to include 2026, update one statistic if possible. Republish. | 🟡 Medium | 45 | ⏳ Pending
40 | May 19 | Week 6 | Phase 5 | On-Page SEO | Internal link audit — add links across the site to low-traffic pages | Every page should have at least 3–5 internal links pointing to it. Pages with zero or one internal link get crawled less frequently and rank lower. Think of internal links as 'votes' within your own site. | Check Google Analytics (or GSC) for pages with <50 clicks. For each: find 2–3 relevant pages that should naturally link to it → Add contextual links within the body text → Not just in navigation or footers. | 🟡 Medium | 60 | ⏳ Pending
41 | May 20 | Week 6 | Phase 3 | Backlinks | Post 5 new Quora answers (second batch — different questions) | Quora answers have a long shelf life. An answer posted today can continue to receive upvotes and appear in Google results for months or years. | Search new questions: 'what is universal life insurance canada', 'should I get life insurance in my 30s canada', 'life insurance for smokers canada', 'rrsp vs life insurance canada', 'mortgage protection insurance worth it canada'. Answer with 400+ words, include link naturally. | 🟡 Medium | 60 | ⏳ Pending
42 | May 21 | Week 6 | Phase 4 | Social Media | Post 3 LinkedIn + 3 Facebook posts (second batch) | Social signals (shares, engagement) are indirect ranking factors. More importantly, consistent posting keeps InsuredCan visible to your target audience and builds brand recognition. | LinkedIn: post on RRSP vs life insurance, life insurance for smokers, cost of life insurance in Ontario. Facebook: repost the Calculator CTA with different hook, newcomers update, critical illness story angle. All from Master Plan content. | 🟡 Medium | 45 | ⏳ Pending
43 | May 22 | Week 7 | Phase 3 | Backlinks | Publish 2 more Medium articles (second batch) | Building a body of content on Medium creates a network effect — readers of one article discover others, and Google trusts the author profile more with each published piece. | Article 6: 'No-Medical Life Insurance Canada: Who Should Get It and Why' → link to /blog/no-medical-life-insurance-canada. Article 7: 'RRSP vs TFSA vs Life Insurance: The Canadian Comparison' → link to /blog/rrsp-tfsa-vs-life-insurance-canada | 🟡 Medium | 90 | ⏳ Pending
44 | May 23 | Week 7 | Phase 3 | Backlinks | Post 3 Reddit responses (new threads — different angles) | Different subreddits have different audiences. r/PersonalFinanceCanada (main), r/CanadaFinance, and r/ontario are all appropriate for insurance answers. | Search r/PersonalFinanceCanada and r/ontario for: 'life insurance recommendations canada 2026', 'critical illness insurance worth it', 'insurance broker vs bank canada'. Post helpful, non-promotional answers with your site link where relevant. | 🟡 Medium | 40 | ⏳ Pending
45 | May 24 | Week 7 | Phase 7 | Review | Mid-point review (Day 45) — analyze what's working | Mid-point review is critical. Without data-driven course correction at day 45, you may spend days 46–90 doing things that aren't moving the needle. | Check GSC: which keywords appeared in top 20 for first time? Check Google Analytics: which referral sources sent traffic? Which Quora/Medium articles drove clicks? Update Dashboard sheet KPIs. Decide: double down on what worked, stop what didn't. | 🔴 High | 90 | ⏳ Pending
46 | May 25 | Week 7 | Phase 8 | Authority | Set up Google Analytics 4 (GA4) for insuredcan.ca if not already configured | GA4 tracks user behavior (time on page, bounce rate, conversions). This data helps you understand which pages users actually find valuable, guiding where to invest content effort. | analytics.google.com → Create property → Add web data stream → Copy gtag.js code → In Lovable: add to index.html head section. Set up a conversion event for 'form_submit' to track quote requests. | 🟡 Medium | 45 | ⏳ Pending
47 | May 26 | Week 7 | Phase 8 | Authority | Research and compile list of Canadian finance blogs for guest post outreach | Guest posts on established sites (Ratehub.ca, MoneySense, Savvy New Canadians, Million Dollar Journey) create powerful backlinks. One guest post on a DA 60+ site outweighs 50 directory citations. | Search Google: 'write for us' + 'life insurance canada' + site:moneysense.ca/contribute. Find: Ratehub.ca, MoneySense.ca, SavvyNewCanadians.com, MillionDollarJourney.com, YoungAndThrifty.ca. Record their 'write for us' page URLs. | 🟡 Medium | 45 | ⏳ Pending
48 | May 27 | Week 7 | Phase 8 | Authority | Write and send 3 guest post pitches to Canadian finance blogs | A guest post pitch should be 150–200 words: introduce yourself, propose 2–3 specific article ideas, explain why their audience would benefit. Personalize each one. | Send to: SavvyNewCanadians.com (great for newcomers content), YoungAndThrifty.ca (great for young professionals), MillionDollarJourney.com (great for whole life/estate content). Pitch InsuredCan as a licensed broker with expertise to share. Propose specific article titles. | 🟡 Medium | 60 | ⏳ Pending
49 | May 28 | Week 7 | Phase 8 | Authority | Set up HARO / Connectively account and respond to 3 insurance queries | HARO (now Connectively) sends daily emails from journalists needing expert sources. A single quote in a major publication (Globe and Mail, Toronto Star, CBC) creates a powerful backlink and brand mention. | Sign up at connective.com as a source (free). Select categories: Business, Financial, Lifestyle. When you receive queries mentioning insurance, mortgages, or personal finance, respond with a brief expert quote and your credentials. Respond within 2 hours for best results. | 🟡 Medium | 30 | ⏳ Pending
50 | May 29 | Week 8 | Phase 8 | Authority | Follow up on guest post pitches + respond to any HARO queries | Most guest post pitches require 1–2 follow-ups before getting a response. A polite follow-up after 5–7 days is standard practice and doubles acceptance rates. | Send follow-up emails: 'Hi [Name], just following up on my pitch from [date]…'. Keep it brief. Check Connectively for new queries daily — set up email alerts for keywords: insurance, life insurance, health insurance, financial planning. | 🟢 Low | 20 | ⏳ Pending
51 | May 30 | Week 8 | Phase 8 | AEO | Add HowTo schema to Coverage Calculator page | HowTo schema tells Google that a page contains step-by-step instructions. This can trigger a rich result in search with numbered steps shown directly in the SERP — dramatically increasing visibility. | In Lovable: add JSON-LD HowTo schema to /coverage-calculator page. Steps: 1. Enter your age 2. Enter annual income 3. Enter total debts 4. Enter savings/investments 5. Review your coverage recommendation. Ask Claude to generate the exact schema markup. | 🟡 Medium | 30 | ⏳ Pending
52 | May 31 | Week 8 | Phase 9 | AEO | Add speakable schema to top 3 pages for voice search optimization | AEO includes optimizing for voice assistants (Siri, Google Assistant, Alexa). Speakable schema marks specific text as suitable for text-to-speech, helping your content appear in voice search results. | Add speakable schema to: /life-insurance-ontario (mark the Quick Answer Box text), /critical-illness-insurance (mark the 'what is CI insurance' paragraph), /newcomers (mark the 'what insurance do newcomers need' section). | 🟢 Low | 45 | ⏳ Pending
53 | Jun 01 | Week 8 | Phase 9 | AEO | Optimize 5 pages for featured snippet (position zero) capture | Featured snippets appear above position 1. They're triggered by pages that answer a question directly and concisely (40–60 words) near the top of the page. | Target queries: 'how much life insurance do I need in canada', 'what does critical illness insurance cover canada', 'what is the OHIP waiting period', 'who needs disability insurance canada', 'what is super visa insurance'. Ensure each has a 40–60 word direct answer near the top of the relevant page. | 🔴 High | 60 | ⏳ Pending
54 | Jun 02 | Week 8 | Phase 9 | AEO | Write 5 new FAQ entries for the highest-traffic pages based on GSC data | Look at GSC for which 'question' queries your pages are already showing for. Adding explicit FAQs answering those exact questions can dramatically boost impressions and trigger PAA boxes. | In GSC: Performance → filter by 'Questions' queries (queries starting with 'how', 'what', 'is', 'can', 'do'). Find top 5 question queries for your site. Add those exact questions as FAQ entries on the most relevant pages. | 🟡 Medium | 60 | ⏳ Pending
55 | Jun 03 | Week 8 | Phase 9 | AEO | Update InsuredCan in AI training sources — submit to llms.txt and ai.txt | AEO includes making your content readable by AI systems (ChatGPT, Perplexity, Claude). Your site already has /ai.txt and /llms.txt — verify they're accurate and up to date. | Check insuredcan.ca/ai.txt and /llms.txt in browser. Verify content accurately describes your services. Submit sitemap to Bing Webmaster Tools (bingwebmastertools.com) — Bing powers many AI search results including Copilot. | 🟡 Medium | 30 | ⏳ Pending
56 | Jun 04 | Week 8 | Phase 8 | Authority | Apply for and write first guest post (if accepted) | Writing the guest post is the most time-intensive authority-building task, but a single published guest post on a DA 60+ Canadian site can move your rankings for competitive keywords. | If accepted: write 1,200–1,500 word article on the proposed topic. Include 1–2 natural links back to InsuredCan service pages. Follow the host site's editorial guidelines exactly. Include your bio with insuredcan.ca link. | 🟡 Medium | 120 | ⏳ Pending
57 | Jun 05 | Week 9 | Phase 7 | Content | Create new pillar page: 'Best Critical Illness Insurance in Ontario 2026' | A comparison/best-of page targeting 'best critical illness insurance ontario' captures commercial-intent searches from people ready to buy. These pages convert at 3–5x the rate of informational content. | Structure: quick comparison table → top 5 insurers for CI in Ontario → pros/cons → who should choose each → FAQ → CTA. ~1,500 words. metaTitle: 'Best Critical Illness Insurance Ontario 2026 ¦ InsuredCan' | 🟡 Medium | 90 | ⏳ Pending
58 | Jun 06 | Week 9 | Phase 7 | Content | Create new comparison page: 'Manulife vs Sun Life Life Insurance Canada' | Brand comparison queries ('Manulife vs Sun Life') are high-intent. People searching this are actively comparing before buying. These pages rank faster because they have clear commercial intent. | Structure: quick verdict → side-by-side comparison table (price, coverage, riders, service) → who each is best for → recommendation → link to free quote. ~800 words. | 🟡 Medium | 90 | ⏳ Pending
59 | Jun 07 | Week 9 | Phase 7 | Content | Publish new comparison pages + add to internal navigation | New pages must be linked from the site to get crawled. Add the CI Ontario page to /critical-illness-insurance and the Manulife vs Sun Life page to the Compare section. | In Lovable: publish both pages. Add navigation links. Update App.tsx with new routes. Update sitemap. | 🔴 High | 30 | ⏳ Pending
60 | Jun 08 | Week 9 | Phase 8 | Review | Week 8 Review — major checkpoint | By week 8, you should see first meaningful ranking movements. Check if early-action keywords (city pages, blog posts) have appeared in top 20. Identify your 'quick wins' and 'slow movers'. | GSC: Performance → Compare to 8 weeks ago. Which queries gained impressions? Which pages got first-click traffic? GA4: Which pages have highest engagement rate? Dashboard: Update all KPIs. Plan final 30 days based on data. | 🔴 High | 90 | ⏳ Pending
61 | Jun 09 | Week 9 | Phase 9 | AEO | Add structured data (Organization schema) to homepage | Organization schema tells AI systems and Google exactly who InsuredCan is, what it does, where it's located, and how to contact it. This strengthens your Knowledge Panel and entity recognition. | Already exists in Index.tsx — verify it includes: name, url, logo, description, contactPoint (with telephone), areaServed (Ontario, Canada), sameAs (links to social profiles and directory listings). Add sameAs for new directory listings. | 🟡 Medium | 30 | ⏳ Pending
62 | Jun 10 | Week 9 | Phase 9 | AEO | Add InsuredCan to Wikidata + local entity databases | Wikidata is a machine-readable knowledge base that Google, AI systems, and search engines use to understand entities. Adding InsuredCan creates an entity record that strengthens brand signals. | Go to wikidata.org → Create account → Create new item: InsuredCan → Add properties: instance of (insurance company), country (Canada), official website, industry, headquarters location. This takes 20 minutes and lasts forever. | 🟢 Low | 30 | ⏳ Pending
63 | Jun 11 | Week 9 | Phase 8 | Authority | Submit to 5 more Canadian business directories | Citation breadth (having consistent NAP across many directories) is a key local SEO factor. Aim for 20–30 unique citations in your first 90 days. | Submit to: InsuranceHotline.com, CanadianInsuranceQuotes.ca, FSRA.on.ca advisor lookup, Better Business Bureau Canada (bbb.org/canada), Chamber of Commerce (occ.ca). Use exact same NAP template. | 🟡 Medium | 60 | ⏳ Pending
64 | Jun 12 | Week 10 | Phase 7 | GEO | Create 3 more Ontario city pages: Guelph, St. Catharines, Sudbury | The more Ontario city pages you have, the stronger your geographic coverage signal to Google. Aim for coverage of all cities with 50,000+ population in Ontario. | Guelph: /life-insurance-guelph (population 135K, university town). St. Catharines: /life-insurance-st-catharines (Niagara region). Sudbury: /life-insurance-sudbury (Northern Ontario presence). Same template process as before. | 🟢 Low | 90 | ⏳ Pending
65 | Jun 13 | Week 10 | Phase 7 | GEO | Publish Guelph, St. Catharines, Sudbury pages + update Ontario hub grid | Each new city page should link to the Ontario hub (/life-insurance-ontario) AND the Ontario hub should link back. This creates a 'hub and spoke' structure that Google rewards. | Publish via Lovable. Add to App.tsx. Add to /life-insurance-ontario city grid. Add to sitemap. Update footer if needed. | 🟡 Medium | 30 | ⏳ Pending
66 | Jun 14 | Week 10 | Phase 5 | Technical SEO | Build out author bio / About page for E-E-A-T signals | Google's E-E-A-T (Experience, Expertise, Authoritativeness, Trustworthiness) framework rewards sites where real experts are identifiable. An author bio with credentials directly improves your trust score. | Update /about page with: founder's name and credentials, insurance license number (FSRA), years of experience, photo, professional background. Add structured data for Person schema. Link to LinkedIn profile. | 🔴 High | 60 | ⏳ Pending
67 | Jun 15 | Week 10 | Phase 5 | Technical SEO | Add testimonial/review schema to homepage and key service pages | Review schema displays star ratings in Google search results. Even 3–4 reviews with schema enabled can add a star rating to your search listing, dramatically increasing CTR. | Ask 3–5 real clients or colleagues for Google reviews. Add Review or AggregateRating schema to homepage. Use ratings you've actually earned — never fake reviews (Google penalizes this). | 🔴 High | 45 | ⏳ Pending
68 | Jun 16 | Week 10 | Phase 8 | Authority | Post second guest post follow-up + research new pitch targets | Guest post outreach is a numbers game. Most sites require 2–3 follow-ups. Meanwhile, continuously adding new targets keeps your pipeline full. | Follow up on original 3 pitches. Research 3 new targets: RateSpy.com, Boomer & Echo (Canadian personal finance blog), DollarVersity. Draft personalized pitches with different article angles than your first batch. | 🟢 Low | 30 | ⏳ Pending
69 | Jun 17 | Week 10 | Phase 3 | Backlinks | Third Quora batch: 5 more answers targeting high-volume queries | By this point you have 15 Quora answers. Aim for 25+ by day 90. Each answer is a permanent traffic source that compounds over time. | New questions: 'best insurance broker canada reddit', 'critical illness insurance vs disability insurance canada', 'life insurance for seniors no medical exam canada', 'travel insurance canada ohip', 'group insurance vs individual canada' | 🟡 Medium | 60 | ⏳ Pending
70 | Jun 18 | Week 10 | Phase 9 | AEO | Audit all pages for keyword cannibalization | Keyword cannibalization occurs when multiple pages on your site target the same keyword. Google gets confused about which page to rank, splitting ranking power between them. | Use GSC: Performance → Pages → check if multiple pages appear for the same query. Common issue: /life-insurance and /term-life-insurance both ranking for 'life insurance canada'. Fix by updating one page's meta to target a different keyword angle. | 🟡 Medium | 45 | ⏳ Pending
71 | Jun 19 | Week 11 | Phase 9 | AEO | Add Breadcrumb schema to all pages | Breadcrumb schema shows the page hierarchy directly in Google search results (Home > Life Insurance > Ontario). This improves CTR and helps Google understand your site structure. | Your site already uses BreadcrumbNav component. Verify it includes the correct JSON-LD schema markup. Add to any pages where it's missing. Breadcrumbs should reflect: Home > Category > Subcategory. | 🟡 Medium | 30 | ⏳ Pending
72 | Jun 20 | Week 11 | Phase 5 | Technical SEO | Update all 'Last Updated' dates in blog posts | Adding or updating a 'Last Updated' date tells Google and readers that the content is current. Google shows dates in search results, and users click more on recent content. | In Lovable: update the metadata/frontmatter of each blog to include 'Last Updated: April 2026'. Add a visible 'Updated: April 2026' line near the top of each blog article body text. | 🟡 Medium | 30 | ⏳ Pending
73 | Jun 21 | Week 11 | Phase 4 | Social Media | Create and post insurance infographic on LinkedIn + Facebook | Visual content (infographics) gets 3x more shares than text content on social media. A shareable infographic can generate natural backlinks when other sites embed it. | Create an infographic: 'Ontario Life Insurance Coverage Calculator — How Much Do You Need?' showing the 10x income formula. Use Canva (free). Post on LinkedIn and Facebook. Add to relevant blog posts on the site. | 🟡 Medium | 60 | ⏳ Pending
74 | Jun 22 | Week 11 | Phase 8 | Authority | Request Google reviews from existing clients | Google reviews directly improve your Business Profile visibility and trust. More reviews also strengthen your E-E-A-T signals. Even 5–10 authentic reviews make a measurable difference. | Send a personal email to past clients or contacts who've used InsuredCan's services: 'It would mean a lot if you could leave a quick Google review. Here's the direct link: [GBP review link]'. Include 3 sentences max. Don't incentivize reviews. | 🔴 High | 30 | ⏳ Pending
75 | Jun 23 | Week 11 | Phase 8 | Review | Week 11 checkpoint — major ranking analysis | By week 11, your initial Quora and Medium links have aged enough to pass authority. City pages should be indexed. Check for 'almost there' keywords (positions 11–20) that need a push. | Focus on: keywords positions 11–20 in GSC (one good backlink or content update can push these to page 1). Identify which city pages ranked. Check if any featured snippets were captured. Update Dashboard KPIs. | 🔴 High | 90 | ⏳ Pending
76 | Jun 24 | Week 11 | Phase 9 | AEO | Double down on best-performing keywords — add more content depth | Once you know which keywords are ranking (positions 5–15), the fastest way to reach position 1–3 is to make that page more comprehensive and authoritative than competitors. | Take your top 3 improving keywords from GSC. For each: open the target page → compare word count and depth vs. the current #1 result → add missing content: more FAQs, a cost table, a comparison, a case study, more internal links. | 🔴 High | 90 | ⏳ Pending
77 | Jun 25 | Week 11 | Phase 7 | Content | Write blog: 'Life Insurance for New Immigrants to Ontario 2026' | Immigrant communities are underserved by insurance content. Content that addresses their specific concerns (immigration status, no credit history, language barriers) ranks faster due to lower competition. | Structure: Can immigrants get life insurance → which immigration status qualifies → best providers for newcomers → super visa insurance → cost examples. Target: 'life insurance new immigrants ontario'. Link to /newcomers and /life-insurance-pr-holders. | 🟡 Medium | 90 | ⏳ Pending
78 | Jun 26 | Week 12 | Phase 7 | Content | Write blog: 'Group Benefits vs Individual Insurance: What Self-Employed Canadians Need to Know' | This targets a decision-stage query from self-employed people choosing between coverage options. High conversion intent, low competition. | Structure: What group benefits include → What they lack → Individual insurance options → Cost comparison → CTA to /self-employed. Target: 'group benefits vs individual insurance canada'. | 🟡 Medium | 90 | ⏳ Pending
79 | Jun 27 | Week 12 | Phase 8 | Authority | Submit InsuredCan to insurance-specific directories + associations | Insurance-specific directories (InsuranceHotline, RatesDotCa advisor section, CLHIA) have very high topical relevance. Links from topically relevant sites pass more SEO value than generic directories. | Submit to: RatesDotCa (rates.ca/life-insurance), InsuranceHotline.com, LifeInsuranceCanada.com advisor directory, InsuranceAdvisors.ca. Also: check if ADVOCIS (advisors.ca) membership directory is available. | 🟡 Medium | 45 | ⏳ Pending
80 | Jun 28 | Week 12 | Phase 3 | Backlinks | Post 5 Quora answers (fourth batch) | Your Quora presence now spans 3–4 weeks. Answers from week 1 may have started earning upvotes. Respond to any comments on existing answers to boost their visibility. | Check existing Quora answers for comments — respond to all. Post 5 new answers: 'term life insurance vs mortgage protection canada', 'life insurance for stay at home parent canada', 'how long does life insurance take to pay out canada', 'can I have multiple life insurance policies canada', 'life insurance waiting period canada' | 🟡 Medium | 60 | ⏳ Pending
81 | Jun 29 | Week 12 | Phase 4 | Social Media | Post 5 LinkedIn + 5 Facebook posts (final social batch) | Consistent social posting over 90 days builds a content library that continues driving organic reach. Your best-performing post should be identified by now and replicated. | LinkedIn: identify which of your first 10 posts got the most engagement → Create 2 similar variations. Post 3 new educational posts. Facebook: Same strategy. Boost one Facebook post with $10–20 targeting Ontario homeowners 30–55. | 🟡 Medium | 45 | ⏳ Pending
82 | Jun 30 | Week 12 | Phase 6 | On-Page SEO | Refresh meta descriptions based on GSC CTR data | After 60+ days, you have real CTR data in GSC. Pages with <2% CTR need new meta descriptions. Pages with >8% CTR — study what made them work and apply to others. | GSC → Performance → by Page → sort by CTR ascending. For the 10 pages with lowest CTR: rewrite meta descriptions using the click-driving angles from Phase 6 of the Master Plan. Focus on: including a price ($25/mo), a benefit ('tax-free'), a time ('60 seconds'). | 🔴 High | 60 | ⏳ Pending
83 | Jul 01 | Week 12 | Phase 9 | AEO | Submit InsuredCan to Perplexity AI and ChatGPT knowledge training | AI chatbots are increasingly answering insurance questions. Getting InsuredCan mentioned in AI-readable sources (structured data, authoritative references) ensures you appear in AI-generated answers. | Submit sitemap to Bing Webmaster (bingwebmastertools.com) — Bing powers Copilot AI. Update /llms.txt and /ai.txt with comprehensive service descriptions. Post content on platforms AI models are known to index (Reddit, Quora, Wikipedia edits where relevant). | 🟢 Low | 30 | ⏳ Pending
84 | Jul 02 | Week 12 | Phase 7 | Content | Create final 2 linkable assets: 'Ontario Insurance Cost Calculator FAQ' + 'Super Visa Insurance Checklist' | Linkable assets are pieces of content that other websites naturally want to link to. A checklist or comprehensive FAQ is more likely to be referenced than a standard service page. | Super Visa Insurance Checklist: 1-page HTML page listing all IRCC requirements, coverage minimums, recommended providers, application steps. This will get links from immigration forums and blogs. Publish at /super-visa-insurance-checklist. | 🟡 Medium | 90 | ⏳ Pending
85 | Jul 03 | Week 13 | Phase 5 | Technical SEO | Final technical SEO audit — fix any remaining issues | After 90 days of changes, a final technical audit catches issues that accumulated: broken internal links from removed content, duplicate title tags from new pages, canonical issues. | Crawl site with free tool (Screaming Frog free tier or Sitechecker.pro) — check for: 404 errors, duplicate title tags, missing meta descriptions, broken links, redirect chains. Fix any issues found via Lovable. | 🔴 High | 60 | ⏳ Pending
86 | Jul 04 | Week 13 | Phase 5 | Technical SEO | Verify Google Business Profile is fully complete and has first reviews | An incomplete GBP listing (missing hours, no photos, no description) ranks lower in the local pack. Ensure all fields are 100% complete and at least 5 reviews have been received. | Check GBP: add 5+ photos (office, team, logo), ensure hours/description are complete, respond to any reviews received. Add 'Insurance Broker' as primary category, 'Life Insurance' and 'Health Insurance' as secondary categories. | 🟡 Medium | 30 | ⏳ Pending
87 | Jul 05 | Week 13 | Phase 4 | Social Media | Create 30-day social content calendar for Days 91–120 | The #1 mistake with social media: stopping after the initial burst. Plan 30 more days of posts now, while momentum is high, to ensure continuity of effort. | Use the Master Plan social content as a template. Create 10 new LinkedIn post drafts and 10 new Facebook post drafts for the next 30 days. Schedule using LinkedIn's built-in scheduler or Buffer (free tier). | 🟡 Medium | 60 | ⏳ Pending
88 | Jul 06 | Week 13 | Phase 8 | Authority | Secure at least one external publication mention | A single mention or quote in a major Canadian publication (MoneySense, CBC News, Toronto Star, Globe and Mail) can move your domain authority 5–10 points overnight. | Check Connectively for any outstanding journalist requests. If any Medium or guest post articles were published, share them with the publications' social media with tags. Reach out to local Toronto/Ontario insurance reporters with a newsworthy angle. | 🟡 Medium | 45 | ⏳ Pending
89 | Jul 07 | Week 13 | Phase 1 | Technical SEO | Final sitemap resubmission + GSC crawl request for all new content | Any content published in the last 30 days should be fresh-submitted to GSC to ensure fast indexing before the 90-day mark. | GSC: resubmit sitemap. URL Inspection: manually submit every new page published in days 31–90 (new blogs, city pages, comparison pages, linkable assets). | 🟡 Medium | 30 | ⏳ Pending
90 | Jul 08 | Week 13 | All Phases | Review | 90-Day Final Review + Plan for Days 91–180 | This is your most important day. Document everything: rankings before vs. after, traffic before vs. after, backlinks built, pages indexed. This becomes your baseline for the next 90 days. | Complete all KPI rows in Dashboard sheet. Write 'What Worked' and 'What Didn't' in the final Weekly Review tab. Identify your top 10 ranking keywords. Plan the next 90-day sprint: double down on winners, cut losers, add new city pages and blogs based on GSC data. | 🔴 High | 120 | ⏳ Pending

## 🎯 Keyword Tracker
InsuredCan — Keyword Ranking Tracker
Update ranking positions weekly from Google Search Console → Performance → Queries
Keyword | Target Page | Monthly Volume | Difficulty | Target Rank | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Notes
life insurance ontario | /life-insurance-ontario | 1,600+ | Medium | Top 5
life insurance toronto | /life-insurance-toronto | 1,300+ | Medium | Top 5
best life insurance canada | / | 2,400+ | High | Top 10
term life insurance canada | /term-life-insurance | 1,900+ | High | Top 10
critical illness insurance canada | /critical-illness-insurance | 800+ | Medium | Top 10
super visa insurance canada | /blog/super-visa-insurance-canada | 1,200+ | Medium | Top 5
cheapest life insurance canada 2026 | /blog/cheapest-life-insurance-canada-2026 | 800+ | Low | Top 3
life insurance mississauga | /life-insurance-mississauga | 500+ | Low | Top 3
life insurance brampton | /life-insurance-brampton | 400+ | Low | Top 3
life insurance hamilton | /life-insurance-hamilton | 350+ | Low | Top 3
life insurance ottawa | /life-insurance-ottawa | 600+ | Low | Top 5
disability insurance ontario | /disability-insurance | 600+ | Medium | Top 10
disability insurance self employed canada | /self-employed | 400+ | Low | Top 5
funeral insurance canada | /funeral-insurance | 400+ | Low | Top 5
funeral insurance ontario | /funeral-insurance | 200+ | Low | Top 3
insurance broker ontario | /insurance-broker-canada | 600+ | Medium | Top 10
life insurance newcomers canada | /newcomers | 400+ | Low | Top 5
life insurance pr holders canada | /life-insurance-pr-holders | 200+ | Low | Top 3
term vs whole life insurance canada | /compare/term-vs-whole-life | 700+ | Medium | Top 10
critical illness vs disability insurance | /compare/critical-illness-vs-disability | 300+ | Low | Top 5
how much life insurance do i need canada | /blog/how-much-life-insurance-canada | 500+ | Low | Top 5
is life insurance worth it canada | /blog/is-life-insurance-worth-it-canada | 400+ | Low | Top 3
best life insurance ontario 2026 | /blog/best-life-insurance-ontario-2026 | 800+ | Low | Top 3
life insurance family toronto | /blog/life-insurance-family-toronto | 300+ | Low | Top 3
ohip waiting period newcomers | /blog/ohip-waiting-period-newcomers | 600+ | Low | Top 3
life insurance kitchener waterloo | /life-insurance-kitchener-waterloo | 250+ | Low | Top 3
life insurance markham | /life-insurance-markham | 300+ | Low | Top 3
life insurance windsor ontario | /life-insurance-windsor | 200+ | Low | Top 3
life insurance barrie | /life-insurance-barrie | 150+ | Low | Top 3
life insurance oshawa | /life-insurance-oshawa | 150+ | Low | Top 3

## 🔗 Backlink Log
InsuredCan — Backlink Building Log
Log every backlink as it's created. Track DA, link type, and target page. Update weekly.
Date | Platform | Article/Post Title | DA (Est.) | Link Type | Target Page Linked | Anchor Text | Status | Notes
Day 8 | Medium | Why Every Ontario Family Needs Life Insurance in 2026 | DA 95 | DoFollow | /life-insurance-ontario | life insurance ontario | ⏳ Pending | Publish on medium.com
Day 9 | Medium | Critical Illness Insurance: The Coverage Most Canadians Are Missing | DA 95 | DoFollow | /critical-illness-insurance | critical illness insurance canada | ⏳ Pending
Day 10 | Medium | Disability Insurance for Self-Employed Canadians | DA 95 | DoFollow | /self-employed | disability insurance self-employed | ⏳ Pending
Day 11 | Medium | Super Visa Insurance 2026 Guide | DA 95 | DoFollow | /blog/super-visa-insurance-canada | super visa insurance canada | ⏳ Pending
Day 12 | Medium | Term Life vs Whole Life Insurance Canada | DA 95 | DoFollow | /compare/term-vs-whole-life | term vs whole life canada | ⏳ Pending
Day 13 | Quora | Best life insurance company Ontario? | DA 93 | NoFollow | /life-insurance-ontario | InsuredCan | ⏳ Pending
Day 13 | Quora | Life insurance cost 40yr old Canada | DA 93 | NoFollow | / | insuredcan.ca | ⏳ Pending
Day 13 | Quora | Do newcomers qualify for life insurance? | DA 93 | NoFollow | /newcomers | insuredcan.ca/newcomers | ⏳ Pending
Day 13 | Quora | Is critical illness insurance worth it? | DA 93 | NoFollow | /critical-illness-insurance | InsuredCan | ⏳ Pending
Day 13 | Quora | What if I can't pay premiums Canada | DA 93 | NoFollow | / | insuredcan.ca | ⏳ Pending
Day 14 | Quora | OHIP waiting period — what insurance needed | DA 93 | NoFollow | /newcomers | insuredcan.ca/newcomers | ⏳ Pending
Day 14 | Quora | Can self-employed get disability insurance | DA 93 | NoFollow | /self-employed | self-employed insurance | ⏳ Pending
Day 14 | Quora | What is no medical life insurance Canada | DA 93 | NoFollow | /blog/no-medical-life-insurance-canada | no medical life insurance | ⏳ Pending
Day 14 | Quora | Agent vs broker Canada difference | DA 93 | NoFollow | /insurance-broker-canada | insurance broker canada | ⏳ Pending
Day 14 | Quora | Is life insurance payout taxable Canada | DA 93 | NoFollow | /blog/is-life-insurance-taxable-canada | is life insurance taxable | ⏳ Pending
Day 15 | Reddit | r/PersonalFinanceCanada — life insurance how much | DA 91 | NoFollow | /coverage-calculator | insuredcan.ca | ⏳ Pending
Day 15 | Reddit | r/PersonalFinanceCanada — just became PR | DA 91 | NoFollow | /newcomers | insuredcan.ca/newcomers | ⏳ Pending
Day 16 | Reddit | r/PersonalFinanceCanada — self employed sick | DA 91 | NoFollow | /self-employed | insuredcan.ca/self-employed | ⏳ Pending
Day 16 | Reddit | r/PersonalFinanceCanada — bank vs independent | DA 91 | NoFollow | /life-insurance | insuredcan.ca | ⏳ Pending
Day 16 | Reddit | r/PersonalFinanceCanada — insurance at 30 ontario | DA 91 | NoFollow | /young-professionals | insuredcan.ca | ⏳ Pending
Day 43 | Medium | No-Medical Life Insurance Canada | DA 95 | DoFollow | /blog/no-medical-life-insurance-canada | no medical life insurance canada | ⏳ Pending | Second Medium batch
Day 43 | Medium | RRSP vs TFSA vs Life Insurance | DA 95 | DoFollow | /blog/rrsp-tfsa-vs-life-insurance-canada | rrsp vs life insurance | ⏳ Pending
Day 48 | Guest Post | TBD — Canadian Finance Blog | DA 60+ | DoFollow | TBD — service page | InsuredCan | ⏳ Pending | Pitch sent Day 48
Day 50 | Yelp | InsuredCan Business Listing | DA 70 | DoFollow | / | insuredcan.ca | ⏳ Pending | Directory citation
Day 50 | YellowPages | InsuredCan Business Listing | DA 72 | DoFollow | / | insuredcan.ca | ⏳ Pending | Directory citation
Day 50 | 411.ca | InsuredCan Business Listing | DA 68 | DoFollow | / | insuredcan.ca | ⏳ Pending | Directory citation
Day 50 | Cylex | InsuredCan Business Listing | DA 55 | DoFollow | / | insuredcan.ca | ⏳ Pending | Directory citation
Day 50 | n49 | InsuredCan Business Listing | DA 52 | DoFollow | / | insuredcan.ca | ⏳ Pending | Directory citation

## 📍 Directory Tracker
InsuredCan — Directory Submission Tracker (NAP Citations)
Consistent Name/Address/Phone across all directories = stronger local SEO. Log each submission.
Directory | URL | DA | Category | Priority | Date Submitted | Status | Login/Account | Notes
Yelp Canada | biz.yelp.ca | 70 | Insurance Brokers | 🔴 High |  | ⏳ Pending |  | Use NAP template
YellowPages Canada | yellowpages.ca | 72 | Insurance Agents & Brokers | 🔴 High |  | ⏳ Pending
411.ca | 411.ca | 68 | Insurance, Life Insurance | 🔴 High |  | ⏳ Pending
Cylex Canada | cylex.ca | 55 | Insurance Brokers, Financial | 🟡 Medium |  | ⏳ Pending
n49 | n49.com | 52 | Insurance Agents & Brokers | 🟡 Medium |  | ⏳ Pending
Google Business Profile | business.google.com | N/A | Insurance Broker | 🔴 High |  | ⏳ Pending |  | Service area: Ontario
Bing Places | bingplaces.com | N/A | Insurance | 🔴 High |  | ⏳ Pending |  | Powers Copilot AI
Better Business Bureau | bbb.org/canada | 78 | Insurance Brokers | 🟡 Medium |  | ⏳ Pending
InsuranceHotline | insurancehotline.com | 55 | Life Insurance | 🟡 Medium |  | ⏳ Pending
RatesDotCa | rates.ca | 65 | Life Insurance | 🟡 Medium |  | ⏳ Pending
Trustpilot Canada | trustpilot.com | 91 | Financial Services | 🟡 Medium |  | ⏳ Pending |  | Get reviews here
Chamber of Commerce Ontario | occ.ca | 58 | Financial Services | 🟢 Low |  | ⏳ Pending
FSRA Advisor Lookup | fsrao.ca | 72 | Insurance Broker | 🔴 High |  | ⏳ Pending |  | License verification
Facebook Business | facebook.com/business | 96 | Insurance / Financial | 🟡 Medium |  | ⏳ Pending |  | Create FB business page
LinkedIn Company | linkedin.com | 98 | Insurance Broker | 🟡 Medium |  | ⏳ Pending |  | Create company page
Wikidata | wikidata.org | 92 | Insurance Company | 🟢 Low |  | ⏳ Pending |  | Entity creation
Foursquare | foursquare.com | 85 | Professional Services | 🟢 Low |  | ⏳ Pending
Hotfrog Canada | hotfrog.ca | 52 | Insurance | 🟢 Low |  | ⏳ Pending
EZlocal Canada | ezlocal.com | 48 | Insurance Broker | 🟢 Low |  | ⏳ Pending
iBegin | ibegin.com | 45 | Financial Services | 🟢 Low |  | ⏳ Pending
📌 STANDARD NAP — USE EXACTLY THIS ON EVERY DIRECTORY
Business Name |  | InsuredCan
Address |  | Toronto, Ontario, Canada
Phone |  | 1-800-555-4678
Website |  | https://www.insuredcan.ca
Email |  | sahil280389@gmail.com
Primary Category |  | Insurance Broker
Secondary Categories |  | Life Insurance ¦ Health Insurance ¦ Critical Illness Insurance

## 📝 Content Calendar
InsuredCan — 90-Day Content Calendar
Plan and track every piece of content across all channels — blogs, social, Q&A, backlinks
Week | Day | Date | Content Type | Title / Topic | Target Keyword | Target Page | Status | Notes
Week 1 | 1 | Apr 10 | Blog Post | Content audit + plan 3 new blogs | all | site-wide | ⏳ Pending
Week 1 | 2 | Apr 11 | Technical | GSC indexing submission | all | site-wide | ⏳ Pending
Week 1 | 3 | Apr 12 | Technical | GSC indexing submission | all | site-wide | ⏳ Pending
Week 1 | 5 | Apr 14 | Directory | Business profile creation | insurance broker ontario | / | ⏳ Pending
Week 1 | 6 | Apr 15 | Directory | Business profile creation | life insurance ontario | / | ⏳ Pending
Week 1 | 7 | Apr 16 | Directory | Business profile creation | insurance broker toronto | / | ⏳ Pending
Week 2 | 8 | Apr 17 | Medium Article | Why Every Ontario Family Needs Life Insurance in 2026 | life insurance ontario | /life-insurance-ontario | ⏳ Pending
Week 2 | 9 | Apr 18 | Medium Article | Critical Illness Insurance: Coverage Canadians Are Missing | critical illness insurance canada | /critical-illness-insurance | ⏳ Pending
Week 2 | 10 | Apr 19 | Medium Article | Disability Insurance for Self-Employed Canadians | disability insurance self employed | /self-employed | ⏳ Pending
Week 2 | 11 | Apr 20 | Medium Article | Super Visa Insurance 2026: Everything You Need to Know | super visa insurance canada | /blog/super-visa-insurance-canada | ⏳ Pending
Week 2 | 12 | Apr 21 | Medium Article | Term Life vs Whole Life Insurance Canada | term vs whole life canada | /compare/term-vs-whole-life | ⏳ Pending
Week 2 | 13 | Apr 22 | Quora Answer | Best insurer Ontario / cost 40yr / newcomers / CI worth it / premiums | various | various | ⏳ Pending
Week 2 | 14 | Apr 23 | Quora Answer | OHIP wait / self-employed disability / no medical / agent vs broker / taxable | various | various | ⏳ Pending
Week 3 | 15 | Apr 24 | Reddit Post | How much life insurance / PR newcomer / self employed sick | various | various | ⏳ Pending
Week 3 | 16 | Apr 25 | Reddit Post | Bank vs independent / insurance at 30 | various | various | ⏳ Pending
Week 3 | 17 | Apr 26 | LinkedIn Post | Bank vs independent / CI gap / self-employed disability | various | various | ⏳ Pending
Week 3 | 18 | Apr 27 | LinkedIn Post | Newcomers / income math / calculator CTA | various | various | ⏳ Pending
Week 3 | 19 | Apr 28 | LinkedIn Post | Funeral insurance / young professionals / term vs whole / retirement | various | various | ⏳ Pending
Week 3 | 20 | Apr 29 | Facebook Post | Bank vs individual / family protection / newcomers / CI / funeral costs | various | various | ⏳ Pending
Week 3 | 21 | Apr 30 | Facebook Post | Calculator CTA / self-employed / tax-free / Toronto / super visa | various | various | ⏳ Pending
Week 4 | 22 | May 01 | Technical | Update title tags + meta descriptions | all priority pages | 10 pages | ⏳ Pending
Week 4 | 24 | May 03 | Technical | GMB listing creation | insurance broker toronto | / | ⏳ Pending
Week 4 | 25 | May 04 | Technical | Add FAQ structured data | various | 5 pages | ⏳ Pending
Week 4 | 26 | May 05 | Technical | Optimize for PAA boxes | various | 5 pages | ⏳ Pending
Week 4 | 30 | May 09 | Review | GSC data analysis + KPI update | — | — | ⏳ Pending
Week 5 | 31 | May 10 | Blog Post | 7 Insurance Mistakes Canadians Make | insurance mistakes canada | /blog/top-insurance-mistakes-canadians | ⏳ Pending
Week 5 | 32 | May 11 | Blog Post | Health Insurance Ontario 2026: What OHIP Doesn't Cover | ohip doesnt cover ontario | /blog/what-ohip-doesnt-cover | ⏳ Pending
Week 5 | 33 | May 12 | Blog Post | Best Life Insurance for Newcomers to Canada 2026 | life insurance newcomers canada | /blog/insurance-new-immigrants-canada | ⏳ Pending
Week 5 | 34 | May 13 | Blog Post | Publish + internal linking | various | 3 pages | ⏳ Pending
Week 5 | 35 | May 14 | GEO Page | Life Insurance Vaughan | life insurance vaughan | /life-insurance-vaughan | ⏳ Pending
Week 5 | 36 | May 15 | GEO Page | Life Insurance Richmond Hill | life insurance richmond hill | /life-insurance-richmond-hill | ⏳ Pending
Week 5 | 37 | May 16 | GEO Page | Life Insurance Burlington | life insurance burlington | /life-insurance-burlington | ⏳ Pending
Week 5 | 38 | May 17 | GEO Page | Publish Vaughan, Richmond Hill, Burlington | various | 3 pages | ⏳ Pending
Week 6 | 41 | May 20 | Quora Answer | Universal life / 30s Ontario / smokers / RRSP / mortgage protection | various | various | ⏳ Pending
Week 6 | 42 | May 21 | LinkedIn Post | RRSP vs life / smokers / cost Ontario + Facebook 3 posts | various | various | ⏳ Pending
Week 6 | 43 | May 22 | Medium Article | No-Medical Life Insurance / RRSP vs TFSA vs Life Insurance | various | various | ⏳ Pending
Week 6 | 44 | May 23 | Reddit Post | Life insurance recommendations / CI vs disability / broker vs bank | various | various | ⏳ Pending
Week 6 | 45 | May 24 | Review | Deep dive GSC + GA4 analysis + course correction | — | — | ⏳ Pending
Week 7 | 47 | May 26 | Blog Post | Identify 5 Canadian finance blogs for outreach | — | — | ⏳ Pending
Week 7 | 48 | May 27 | Blog Post | Personalized pitches with article ideas | — | — | ⏳ Pending
Week 8 | 53 | Jun 01 | Technical | Add structured data for voice + how-to | coverage calculator | /coverage-calculator | ⏳ Pending
Week 8 | 54 | Jun 02 | Technical | 40–60 word direct answers for PAA | top 5 queries | 5 pages | ⏳ Pending
Week 9 | 57 | Jun 05 | Blog Post | Best Critical Illness Insurance Ontario 2026 | best critical illness insurance ontario | /best-critical-illness-insurance-ontario | ⏳ Pending
Week 9 | 58 | Jun 06 | Blog Post | Manulife vs Sun Life Life Insurance Canada | manulife vs sun life | TBD | ⏳ Pending
Week 10 | 60 | Jun 08 | Review | Major ranking checkpoint — adjust strategy | — | — | ⏳ Pending
Week 10 | 64 | Jun 12 | GEO Page | 3 more Ontario city pages | life insurance guelph/st.catharines/sudbury | 3 pages | ⏳ Pending
Week 10 | 66 | Jun 14 | Technical | Update About page with credentials + schema | — | /about | ⏳ Pending
Week 11 | 69 | Jun 17 | Quora Answer | Brand comparisons / seniors life insurance / multiple policies | various | various | ⏳ Pending
Week 11 | 73 | Jun 21 | LinkedIn Post | Ontario life insurance coverage calculator infographic | — | LinkedIn + Facebook | ⏳ Pending
Week 12 | 76 | Jun 24 | Technical | Add content depth to best-ranking pages | top 3 improving keywords | 3 pages | ⏳ Pending
Week 12 | 77 | Jun 25 | Blog Post | Life Insurance for New Immigrants to Ontario 2026 | life insurance immigrants ontario | /blog/insurance-new-immigrants-canada | ⏳ Pending
Week 12 | 78 | Jun 26 | Blog Post | Group Benefits vs Individual Insurance — Self-Employed Canada | group benefits vs individual canada | TBD | ⏳ Pending
Week 12 | 80 | Jun 28 | Quora Answer | Term vs mortgage / stay at home parent / waiting period / multiple policies | various | various | ⏳ Pending
Week 12 | 81 | Jun 29 | LinkedIn Post | Best performing content variations — LinkedIn + Facebook | various | various | ⏳ Pending
Week 13 | 82 | Jun 30 | Technical | Update low-CTR metas using GSC data | all | 10 pages | ⏳ Pending
Week 13 | 85 | Jul 03 | Technical | Fix any accumulated issues | all | site-wide | ⏳ Pending
Week 13 | 89 | Jul 07 | Technical | Submit all new content to GSC | all | site-wide | ⏳ Pending
Week 13 | 90 | Jul 08 | Review | Full analysis + Q2 planning | — | — | ⏳ Pending

## 📋 Weekly Reviews
InsuredCan — Weekly Review Template
Complete every Monday. Takes 30 minutes. This is the most important habit for ranking growth.
WEEK 1 ¦ April 10 – April 16, 2026
Metric | Target | Actual | Change | ✅ Met?
GSC Total Impressions | +500
GSC Total Clicks | +20
Avg CTR | 2.5%+
Avg Position | <25
Pages Indexed | 70+
New Backlinks this week | 2+
Keywords in Top 20 | 2+
✅ What worked this week?
❌ What didn't work / blockers?
🔑 Top 3 keywords improving? | 1. ¦ 2. ¦ 3.
🎯 Next week's top 3 priorities | 1. ¦ 2. ¦ 3.
💡 Learning / insight from data
❓ Questions to ask Claude
WEEK 2 ¦ April 17 – April 23, 2026
Metric | Target | Actual | Change | ✅ Met?
GSC Total Impressions | +1000
GSC Total Clicks | +40
Avg CTR | 2.5%+
Avg Position | <25
Pages Indexed | 70+
New Backlinks this week | 2+
Keywords in Top 20 | 4+
✅ What worked this week?
❌ What didn't work / blockers?
🔑 Top 3 keywords improving? | 1. ¦ 2. ¦ 3.
🎯 Next week's top 3 priorities | 1. ¦ 2. ¦ 3.
💡 Learning / insight from data
❓ Questions to ask Claude
WEEK 3 ¦ April 24 – April 30, 2026
Metric | Target | Actual | Change | ✅ Met?
GSC Total Impressions | +1500
GSC Total Clicks | +60
Avg CTR | 2.5%+
Avg Position | <25
Pages Indexed | 70+
New Backlinks this week | 2+
Keywords in Top 20 | 6+
✅ What worked this week?
❌ What didn't work / blockers?
🔑 Top 3 keywords improving? | 1. ¦ 2. ¦ 3.
🎯 Next week's top 3 priorities | 1. ¦ 2. ¦ 3.
💡 Learning / insight from data
❓ Questions to ask Claude
WEEK 4 ¦ May 01 – May 07, 2026
Metric | Target | Actual | Change | ✅ Met?
GSC Total Impressions | +2000
GSC Total Clicks | +80
Avg CTR | 2.5%+
Avg Position | <25
Pages Indexed | 70+
New Backlinks this week | 2+
Keywords in Top 20 | 8+
✅ What worked this week?
❌ What didn't work / blockers?
🔑 Top 3 keywords improving? | 1. ¦ 2. ¦ 3.
🎯 Next week's top 3 priorities | 1. ¦ 2. ¦ 3.
💡 Learning / insight from data
❓ Questions to ask Claude
WEEK 5 ¦ May 08 – May 14, 2026
Metric | Target | Actual | Change | ✅ Met?
GSC Total Impressions | +2500
GSC Total Clicks | +100
Avg CTR | 2.5%+
Avg Position | <25
Pages Indexed | 70+
New Backlinks this week | 1+
Keywords in Top 20 | 10+
✅ What worked this week?
❌ What didn't work / blockers?
🔑 Top 3 keywords improving? | 1. ¦ 2. ¦ 3.
🎯 Next week's top 3 priorities | 1. ¦ 2. ¦ 3.
💡 Learning / insight from data
❓ Questions to ask Claude
WEEK 6 ¦ May 15 – May 21, 2026
Metric | Target | Actual | Change | ✅ Met?
GSC Total Impressions | +3000
GSC Total Clicks | +120
Avg CTR | 2.5%+
Avg Position | <25
Pages Indexed | 70+
New Backlinks this week | 1+
Keywords in Top 20 | 12+
✅ What worked this week?
❌ What didn't work / blockers?
🔑 Top 3 keywords improving? | 1. ¦ 2. ¦ 3.
🎯 Next week's top 3 priorities | 1. ¦ 2. ¦ 3.
💡 Learning / insight from data
❓ Questions to ask Claude
WEEK 7 ¦ May 22 – May 28, 2026
Metric | Target | Actual | Change | ✅ Met?
GSC Total Impressions | +3500
GSC Total Clicks | +140
Avg CTR | 2.5%+
Avg Position | <25
Pages Indexed | 70+
New Backlinks this week | 1+
Keywords in Top 20 | 14+
✅ What worked this week?
❌ What didn't work / blockers?
🔑 Top 3 keywords improving? | 1. ¦ 2. ¦ 3.
🎯 Next week's top 3 priorities | 1. ¦ 2. ¦ 3.
💡 Learning / insight from data
❓ Questions to ask Claude
WEEK 8 ¦ May 29 – June 04, 2026
Metric | Target | Actual | Change | ✅ Met?
GSC Total Impressions | +4000
GSC Total Clicks | +160
Avg CTR | 2.5%+
Avg Position | <25
Pages Indexed | 70+
New Backlinks this week | 1+
Keywords in Top 20 | 16+
✅ What worked this week?
❌ What didn't work / blockers?
🔑 Top 3 keywords improving? | 1. ¦ 2. ¦ 3.
🎯 Next week's top 3 priorities | 1. ¦ 2. ¦ 3.
💡 Learning / insight from data
❓ Questions to ask Claude
WEEK 9 ¦ June 05 – June 11, 2026
Metric | Target | Actual | Change | ✅ Met?
GSC Total Impressions | +4500
GSC Total Clicks | +180
Avg CTR | 2.5%+
Avg Position | <25
Pages Indexed | 70+
New Backlinks this week | 1+
Keywords in Top 20 | 18+
✅ What worked this week?
❌ What didn't work / blockers?
🔑 Top 3 keywords improving? | 1. ¦ 2. ¦ 3.
🎯 Next week's top 3 priorities | 1. ¦ 2. ¦ 3.
💡 Learning / insight from data
❓ Questions to ask Claude
WEEK 10 ¦ June 12 – June 18, 2026
Metric | Target | Actual | Change | ✅ Met?
GSC Total Impressions | +5000
GSC Total Clicks | +200
Avg CTR | 2.5%+
Avg Position | <25
Pages Indexed | 70+
New Backlinks this week | 1+
Keywords in Top 20 | 20+
✅ What worked this week?
❌ What didn't work / blockers?
🔑 Top 3 keywords improving? | 1. ¦ 2. ¦ 3.
🎯 Next week's top 3 priorities | 1. ¦ 2. ¦ 3.
💡 Learning / insight from data
❓ Questions to ask Claude
WEEK 11 ¦ June 19 – June 25, 2026
Metric | Target | Actual | Change | ✅ Met?
GSC Total Impressions | +5500
GSC Total Clicks | +220
Avg CTR | 2.5%+
Avg Position | <25
Pages Indexed | 70+
New Backlinks this week | 1+
Keywords in Top 20 | 22+
✅ What worked this week?
❌ What didn't work / blockers?
🔑 Top 3 keywords improving? | 1. ¦ 2. ¦ 3.
🎯 Next week's top 3 priorities | 1. ¦ 2. ¦ 3.
💡 Learning / insight from data
❓ Questions to ask Claude
WEEK 12 ¦ June 26 – July 02, 2026
Metric | Target | Actual | Change | ✅ Met?
GSC Total Impressions | +6000
GSC Total Clicks | +240
Avg CTR | 2.5%+
Avg Position | <25
Pages Indexed | 70+
New Backlinks this week | 1+
Keywords in Top 20 | 24+
✅ What worked this week?
❌ What didn't work / blockers?
🔑 Top 3 keywords improving? | 1. ¦ 2. ¦ 3.
🎯 Next week's top 3 priorities | 1. ¦ 2. ¦ 3.
💡 Learning / insight from data
❓ Questions to ask Claude
WEEK 13 ¦ July 03 – July 09, 2026
Metric | Target | Actual | Change | ✅ Met?
GSC Total Impressions | +6500
GSC Total Clicks | +260
Avg CTR | 2.5%+
Avg Position | <25
Pages Indexed | 70+
New Backlinks this week | 1+
Keywords in Top 20 | 26+
✅ What worked this week?
❌ What didn't work / blockers?
🔑 Top 3 keywords improving? | 1. ¦ 2. ¦ 3.
🎯 Next week's top 3 priorities | 1. ¦ 2. ¦ 3.
💡 Learning / insight from data
❓ Questions to ask Claude

## 📚 SEO Glossary
InsuredCan — SEO/GEO/AEO Glossary (Learn While Doing)
Reference guide: understand every term used in this plan. No jargon left unexplained.
Term | Category | Plain English Definition | Why It Matters for InsuredCan | How to Check / Act On It
Organic Search | SEO | Traffic that comes to your site from unpaid Google results — not ads | This is your main goal. 90%+ of InsuredCan's target traffic should come from organic | GSC → Performance → Search type: Web
GSC (Google Search Console) | SEO | Google's free tool showing how your site appears in search results | The #1 tool for tracking rankings, indexing status, click data, and errors | search.google.com/search-console
Impression | SEO | Every time your page URL appeared in a Google search result (even if not clicked) | Rising impressions = Google is discovering your pages. Needed before clicks happen | GSC → Performance → Impressions column
Click-Through Rate (CTR) | SEO | % of impressions where someone clicked your result. Formula: Clicks ÷ Impressions | Low CTR = your title/meta isn't compelling. Industry avg: 2-5% in insurance | GSC → Performance → CTR column
Average Position | SEO | Your average ranking spot across all search queries. Position 1 = top result | Target: get all priority keywords below position 20 first, then push to top 10 | GSC → Performance → Position column
Indexing | SEO | Google storing and including your page in its search database so it can appear in results | Pages that aren't indexed = invisible to Google. ~70 pages need to be indexed | GSC → Pages → Coverage report
Crawl Budget | SEO | How many pages Google will crawl on your site in a given time period | Orphan pages waste crawl budget. Internal linking ensures Google finds all pages | GSC → Crawl Stats report
Domain Authority (DA) | SEO | A score (0-100) estimating how much Google trusts your domain. Higher = easier to rank | New sites start at DA 1-10. Getting to DA 20-30 in 90 days = strong progress | Check: moz.com/link-explorer (free)
Backlink | SEO | A link from another website pointing to your site. Google treats these as votes of trust | Every backlink from Medium (DA 95), Quora (DA 93) improves InsuredCan's authority | Check: GSC → Links section
DoFollow vs NoFollow | SEO | DoFollow links pass SEO value. NoFollow links don't pass value but drive traffic | Medium = DoFollow. Quora/Reddit = NoFollow. Both matter for growth | No tool needed — NoFollow links still drive real traffic
NAP | Local SEO | Name, Address, Phone — your business contact info as it appears across the web | Inconsistent NAP (e.g., different phone number on different sites) confuses Google's local algorithm | Check: yextpages.com/scan for NAP inconsistencies
Local Pack | Local SEO | The map + 3 business listings that appear at the top of local searches | Appearing in the Local Pack for 'life insurance toronto' = massive visibility boost | Requires Google Business Profile + citations + reviews
Citation | Local SEO | Any online mention of your business NAP — on directories, blogs, or news sites | 30+ consistent citations = strong local authority signal for Ontario searches | Track in Directory Tracker sheet
Google Business Profile (GBP) | Local SEO | Google's business listing tool — creates your presence in Maps and Local Pack | Essential for local pack visibility. Even online brokers can have a service area listing | business.google.com
E-E-A-T | SEO | Experience, Expertise, Authoritativeness, Trustworthiness — Google's quality framework | Insurance is a YMYL (Your Money Your Life) topic. Google holds it to higher E-E-A-T standards | Add author bios, credentials, FSRA license number to site
YMYL | SEO | Your Money Your Life — categories Google holds to higher quality standards (finance, health, legal) | Insurance = YMYL. You need credibility signals: license info, author bios, citations | Add FSRA license info + advisor credentials to site
Title Tag | On-Page SEO | The clickable blue headline shown in Google search results — max 60 characters | #1 on-page ranking factor. Updated in metaTitle prop in your Lovable pages | GSC → Performance → see which titles have low CTR
Meta Description | On-Page SEO | The 155-char summary below the title in search results. Not a ranking factor but drives CTR | Better meta = more clicks = higher CTR = indirect ranking boost | GSC → Performance → pages with low CTR need new metas
Featured Snippet | AEO | The boxed answer at position zero in Google, above all regular results | Capturing featured snippets for 'how much life insurance canada' = massive exposure | Structure content with direct 40–60 word answers to questions
People Also Ask (PAA) | AEO | The expandable question boxes that appear in most Google searches | Insurance queries have 4–8 PAA boxes. Appearing there = huge visibility without ranking #1 | Add FAQ sections answering the exact PAA questions for your keywords
Schema Markup | AEO | Code added to pages that tells Google/AI the meaning and type of your content | FAQ schema creates expandable Q&As in results. HowTo schema shows numbered steps | Ask Claude to generate JSON-LD schema code for any page
AEO (Answer Engine Optimization) | AEO | Optimizing content to appear in AI-generated answers (ChatGPT, Perplexity, Google AI Overviews) | AI assistants are answering more insurance questions directly. Your content must be structured for machine reading | Create direct Q&A content, add schema, submit to llms.txt
GEO (Geo Optimization) | GEO | Creating location-specific content to rank for '[service] + [city]' searches | 'Life insurance toronto', 'insurance broker mississauga' — these convert better than generic queries | Build city pages for every Ontario city with 50K+ population
Keyword Cannibalization | SEO | When multiple pages on your site compete for the same keyword, splitting Google's ranking signal | Can cause your own pages to fight each other. Fix by differentiating targets per page | Check GSC: if 2+ pages rank for same query
Internal Link | SEO | A link from one page on your site to another page on your site | Distributes PageRank, helps Google discover pages, tells Google which pages are most important | Every page should have 3–5 internal links pointing to it
Orphan Page | SEO | A page with no internal links pointing to it — hard for Google to find and rank | City pages like /life-insurance-barrie may be orphans if not linked from Ontario hub | Check: Screaming Frog free version → orphan detection
Sitemap | SEO | An XML file listing all your pages, submitted to Google to guide crawling | Without it, Google discovers pages slowly by following links. With it = structured roadmap | Submit sitemap.xml via GSC → Sitemaps
Core Web Vitals | Technical SEO | Google's speed/usability metrics: LCP, FID, CLS — used as ranking signals | Slow pages rank lower. Lovable-hosted sites are usually fast but worth checking | pagespeed.insights.google.com → enter insuredcan.ca
HARO / Connectively | Authority | Help A Reporter Out — journalists post queries seeking expert sources | One quote in a major publication (Globe and Mail) = powerful backlink + brand mention | connective.com → sign up as source → respond within 2 hours
Guest Post | Authority | Writing an article published on someone else's website with a link back to yours | Highest-quality backlinks. A guest post on Ratehub.ca (DA 70+) moves rankings significantly | Pitch with personalized email + 3 specific article ideas
Canonical Tag | Technical SEO | HTML tag telling Google which version of a page is the 'official' one | Prevents duplicate content issues when similar pages exist (e.g., with/without www) | View page source → search 'canonical' → verify URL is correct
301 Redirect | Technical SEO | Permanent redirect from one URL to another — passes 100% of link equity | If you change a page URL, a 301 redirect ensures old links still work | Check for redirect chains in Screaming Frog
Topical Authority | SEO | Google's trust in your site as an expert on a specific topic — built by covering it comprehensively | Covering all aspects of Canadian insurance (life, health, CI, disability, city pages) builds topical authority | Create a full content cluster around each insurance type